## Slide 1
Enterprise Backup Platform — Client Kickoff
Resilience workstream | Current Azure foundation with future multi-cloud expansion
PRIMARY OBJECTIVE
Establish an enterprise-grade backup and recovery platform for Azure now, with a design that can extend to AWS without re-architecting the operating model.
REGIONAL MODEL
Canada Central
Primary production region
Canada East
Secondary DR / recovery target
1
Current state
Azure is the immediate scope
Azure-native backup is currently in place
Backup design now needs enterprise governance, security and recovery standards
2
Target state
End-to-end coverage across IaaS, PaaS and SaaS
Centralized policy, retention, monitoring and recovery governance
Protection of critical workloads across Canada regions
DESIGN PRINCIPLE
Data residency and security first
Backup data should remain within Canada, with resilient copies and strong ransomware / access controls.

## Slide 2
Current-to-Target Scope
What the enterprise platform must protect and how the solution evolves
Azure Workloads
Primary scope today
IaaS: VMs / compute
PaaS: databases / services
SaaS: business data where supported
Enterprise Backup Layer
Common operating model
Policy & retention
Encryption & access control
Monitoring / reporting
Recovery orchestration
Canada Recovery
Resilience by region
Canada Central — primary
Canada East — secondary
Recovery testing / validation
Future AWS Expansion
Phase 2 capability
Extend policy & governance
Protect AWS workloads
Maintain Canada-only data residency
Unified operational reporting
Key outcome
A single enterprise backup strategy that meets today’s Azure requirements and can absorb AWS workloads later.

## Slide 3
Enterprise Backup Platform — What This Workstream Will Deliver
Assessment + requirements gathering to establish the path forward
Our immediate objective is to understand the environment, capture requirements, and align on the solution direction before any design or implementation begins.
01
ASSESS
Current state
Inventory workloads, existing Azure-native backup, recovery practices, dependencies, gaps and constraints.
02
DEFINE
Requirements
Establish IaaS / PaaS / SaaS coverage, RPO/RTO, retention, security, residency, operational and recovery requirements.
03
ALIGN
Path forward
Evaluate solution options, identify changes required to existing workloads, and agree the recommended direction.
SCOPE BOUNDARY
Design & implementation are not part of this phase. Once solution alignment is reached, a Change Request (CR) will be executed for the next phase.
CLIENT INPUTS NEEDED TO KEEP THE ASSESSMENT MOVING
✓
Timely access to relevant environments, tools and documentation
✓
Workload / application inventory and business criticality
✓
Existing backup, recovery, retention and security standards
EXPECTED OUTPUTS FROM THIS WORKSTREAM
→
Agreed assessment findings and current-state gaps
→
Requirements baseline and evaluation criteria
→
Clear recommendation / path forward for the next phase
3

## Slide 4
Project Timeline & Key Milestones
Assessment and requirements are the current SOW; design / implementation are indicative and require CR approval after alignment.
ENTERPRISE BACKUP PLATFORM
Assessment → Requirements Sign-off → CR → Delivery
Phase / Activity
Target Start
Target End
Key Milestone / Outcome
Analysis + discussion
Oct 05
Oct 23
Current-state findings reviewed and confirmed
Requirements gathering
Oct 19
Nov 06
Business, technical, security, residency and recovery requirements captured
Requirements sign-off
Nov 09
Nov 13
Approved requirements baseline • Decision gate for CR
Backup Platform Design*
Nov 16
Nov 27
Target architecture, operating model and migration approach
POC validation*
Nov 30
Dec 11
Candidate platform validated against priority use cases
Design review & approval*
Dec 14
Dec 18
Approved solution direction / implementation readiness
CLIENT HOLIDAY / OFFICE CLOSURE
Dec 21, 2026
Jan 01, 2027
Normal business activities resume Jan 04, 2027
Implementation*
Jan 04
Jan 22
Platform configuration, onboarding and policy implementation
Backup & Recovery Validation*
Jan 25
Feb 05
Recovery testing, controls validation and operational readiness
Knowledge Transfer + Transition*
Feb 08
Feb 19
KT, runbook walkthrough and transition to operations
Stabilization & Acceptance*
Feb 22
Mar 06
Final readiness, stabilization, acceptance and project exit
PLATFORM RECOVERY RUNBOOKS — INDICATIVE POST-CR WORKSTREAM
Jan 25 → Mar 05, 2027
Recovery scenarios
Jan 25–29
Runbook development
Feb 01–12
Tabletop + feedback
Feb 15–19
Finalization + approval
Feb 22–26
Knowledge transfer
Mar 01–05
Current SOW exit
Requirements sign-off / alignment
* Indicative post-CR dates require client alignment, CR approval and scheduling. Holiday: Dec 21, 2026 – Jan 01, 2027.

## Slide 5
Kickoff Discussion — Proposed Agenda
A focused session to align requirements before platform evaluation / POC
1
Business & workload scope
Which workloads are in scope now? What is business-critical?
2
Recovery objectives
Target RPO / RTO, retention, backup frequency, recovery testing expectations
3
Security & residency
Canada-only requirement, encryption, access model, immutability / cyber-recovery expectations
4
Platform requirements
IaaS / PaaS / SaaS coverage, Azure today, AWS readiness tomorrow
5
Evaluation path
Platform shortlist, POC success criteria, decision timeline, ownership and next steps
Expected outputs
Agreed scope
Requirements baseline
POC / evaluation criteria
Action owners & next steps