## Slide 1: Enterprise Cloud Workload Backup and Recovery
KEY DECISION DOCUMENT | STAKEHOLDER WALKTHROUGH
30-minute session to walk through the KDD (v0.6), confirm the recommended approach and agree the next steps
Session outcomes
Understand
the business need, the options assessed and what the KDD recommends
Align
on the recommended approach, its trade-offs and the open conditions
Decide
the decisions needed today and who owns each next step
Agenda
1 Objectives
2 Context and requirements
3 Proposed solution
4 Key capabilities
5 Implementation
6 Decisions
Notes: About 3 minutes. Thank stakeholders for reviewing the KDD that was circulated. Explain that today is not a page-by-page review: we will cover the business need, the recommended approach, its main capabilities, the implementation path, and the decisions we need. Ask attendees to hold detailed technical questions for the Q&A at the end of slides 3 and 6. Expected outcomes: shared understanding, alignment on the recommendation and its conditions, and agreed owners for next steps.

## Slide 2: Business context and key requirements
Where we are today
Canada Central
Primary Azure region, zone-redundant; no workloads in Canada East (capacity)
~100 TB
Azure data protected today, growing ~25% a year
In production
Azure Backup already protects supported Azure workloads
AWS
Possible future cloud; no re-platforming when adopted
What the business needs
Data stays in Canada
Production data, backup copies, replicas and metadata
Isolated offsite copy
A separate copy in Canada; zone redundancy alone is not enough
Rebuild deleted environments
Resource groups, networks and app configuration, not just data
DevOps and GitHub protected
Source code, pipelines and Infrastructure as Code
Entra ID recoverable
Users, groups, apps and access policies after errors or attack
Ransomware-resilient
Immutable backups, multi-person approval, tested recovery
Azure Backup works well for in-region protection today. The gaps come from enterprise-wide needs: isolation, environment rebuild, DevOps, identity and AWS.
Notes: About 5 minutes. Start with the current state: Azure is the main cloud, production is in Canada Central, and Azure Backup is already implemented and working as designed. Stress that the KDD does not position Azure Backup as a poor product. The decision is driven by six enterprise needs on the right. Data residency in Canada is mandatory and covers metadata, not only backup data. Zone redundancy inside Canada Central does not count as an offsite copy. Rebuilding deleted resource groups and networks, protecting DevOps repositories and recovering Entra ID are the main gaps. AWS may be adopted later, so the approach should not need re-platforming.

## Slide 3: Proposed solution: extend Commvault to cloud workloads
RECOMMENDED
Option A: Commvault
Extend the platform already used for on-premises and Microsoft 365
$4.4M
5-year ROM (CAD)
4.0
Decision score / 5
Isolated offsite copy; environment rebuild
DevOps, Entra ID and AWS on one platform
Condition: resolve control-plane residency
NOT RECOMMENDED
Option B: Rubrik
New third-party platform for cloud, alongside Commvault on-premises
$5.4M
5-year ROM (CAD)
3.5
Decision score / 5
Strongest default security
Second enterprise platform to run
Highest cost; rebuild relies on IaC
CREDIBLE LOWER-COST ALTERNATIVE
Option C: Azure Backup
Keep and enhance the native service already in production
$2.3M
5-year ROM (CAD)
3.3
Decision score / 5
Lowest cost; no migration
Offsite copy in the same tenant
7-day native Entra ID recovery; no AWS path
Recommendation: adopt Option A, keeping native Azure PITR for PaaS databases. Option C is the fallback if the residency condition cannot be met, or if AWS is not expected and a same-tenant offsite copy is acceptable.
Notes: About 7 minutes. Three options were assessed in depth; others such as Veeam were screened out because they would add a third platform without filling more gaps (KDD 2.1.5). Option A extends Commvault, which already runs on-premises and Microsoft 365 backup. It scores highest (4.0 of 5) because it closes the isolation, rebuild, DevOps and identity gaps on one platform. It costs about CAD 2.1M more than Option C over five years at ROM accuracy, and its SaaS control plane for Canadian regions is listed in East US 2, so residency must be resolved before approval. Option B adds a second enterprise platform at the highest cost. Option C is the credible lower-cost path: it is already in production, but its offsite copy sits in the same tenant, native Entra ID backups last 7 days, and there is no AWS path. All costs are ROM estimates (−40% / +50%) and must be replaced by quotes and actual Azure Backup spend. Pause for questions here.

## Slide 4: Key capabilities and business benefits (Option A)
One platform, one team
On-premises, Microsoft 365 and cloud backup managed together
Benefit: Simpler operations, one audit trail
Isolated offsite copy in Canada
Immutable copy in a separate tenant, plus an optional on-premises copy
Benefit: Recovery even if production credentials are compromised
Rebuild whole environments
Restores deleted resource groups, networks and app settings, then the data
Benefit: Faster, predictable recovery
DevOps and GitHub protected
Repositories, pull requests, pipelines and work items backed up
Benefit: Source code and IaC are recoverable
Long-term Entra ID recovery
Users, groups, apps and Conditional Access beyond the native 7 days
Benefit: Identity restored after errors or attack
Ready for AWS
Same policies and console when AWS is adopted
Benefit: No re-platforming later
Microsoft-native protection stays in place: Azure PITR / LTR for PaaS databases and Entra Backup and Recovery remain enabled alongside Commvault.
Notes: About 6 minutes. Walk through the six capabilities in business terms rather than technical detail. One platform: the same team, console and audit trail across on-premises, Microsoft 365 and cloud. Isolated offsite copy: backups held in a separate, immutable vendor tenant in Canada, so a compromised production admin cannot delete them. Environment rebuild: Commvault Cloud Rewind recreates deleted resource groups, networks and app configuration before restoring data (to be proven in the PoC; same-region only for selected resources). DevOps: repositories and pipelines protected, with GitHub issues and Actions handled by exports. Entra ID: long-term copies beyond Microsoft's 7-day native window. AWS: same policies when adopted. Native Azure protection is not switched off.

## Slide 5: Implementation approach and next steps
0 Validate
Months 0–2
Residency confirmation, PoC, quotes
1 Quick wins
Months 0–2
DevOps backup, resource locks, hardening
2 Azure onboarding
Months 2–5
Primary and offsite copies; onboard by tier
3 Environment recovery
Months 3–6
Rebuild runbooks; retire Azure Backup policies at expiry
4 AWS
At adoption
Same policies from go-live
Key dependencies before approval
Commvault confirms what metadata leaves Canada (SaaS control plane listed in East US 2); Compliance accepts or rejects
PoC passes for workloads marked "confirm", including environment rebuild, DevOps and Entra ID restore
Commvault quote compared with actual Azure Backup spend from Azure Cost Management
Canada East compute capacity options confirmed for cross-region recovery
~159
person-days of effort (ROM)
4–6
months to full Azure protection
Notes: About 4 minutes. The approach is phased so risk stays low: Azure Backup keeps running until the new protection is proven and old recovery points expire. Phase 0 validates the residency question, runs the PoC and obtains quotes. Phase 1 quick wins apply whichever option is chosen: DevOps backup, resource locks and Azure Policy, and hardening. Phases 2 and 3 onboard Azure workloads, the offsite copy and environment rebuild. AWS is onboarded only when adopted. Highlight the four dependencies; the residency confirmation is the critical path. If Option C were chosen instead, there is no core implementation effort, only about 96 person-days of optional enhancements.

## Slide 6: Key decisions and stakeholder alignment
Decisions required today
1
Endorse Option A
as the recommended direction, subject to the conditions of approval in the KDD
2
Set the residency position
Is Commvault’s SaaS control plane (East US 2) acceptable for metadata? If not, adopt Option C
3
Confirm planning assumptions
AWS adoption timing, Entra ID retention needs and the ~CAD 4.4M (ROM) budget envelope
Open questions
Would Security accept a same-tenant offsite copy (the deciding factor for Option C)?
What is the actual current Azure Backup spend?
Are IaC definitions complete for critical environments?
Action items
Action | Owner | Due
Written residency confirmation from Commvault | Compliance / Procurement | [Date]
Confirm workload status, data volumes and identity count | Cloud and IAM Leads | [Date]
Commvault quote vs. actual Azure Backup spend | Procurement / Finance | [Date]
Run the PoC and report to the Design Authority | Resilience Lead | [Date]
Notes: About 5 minutes, plus remaining time for discussion. Ask for three decisions. First, endorsement of Option A as the direction, subject to the KDD conditions of approval. Second, a clear position on residency: Commvault lists East US 2 as the control plane for its Canadian storage regions, so Privacy and Compliance must decide whether that metadata scope is acceptable; if not, the fallback is Option C. Third, confirm the planning assumptions that drive the choice: AWS timing, Entra ID retention needs and the budget envelope. Capture answers to the open questions and confirm owners and dates for the four actions before closing.