## Sheet1
Estimated Timeline for Enterprise Backup Platform |  |  | Estimated Timeline for Enterprise Backup Platform
Activities | Target Start Date | Target End Date | Activities | Target Start Date | Target End Date
Requirements Defination | Week 1 | Week 2 | Requirements Defination | Oct 05 2026 | Oct 16 2026
Backup Platform Design | Week 2 | Week 3 | Backup Platform Design | Oct 12 2026 | Oct 23 2026
Design Review and Approval | Week 4 | Week 4 | Design Review and Approval | Oct 26 2026 | Oct 30 2026
Platform Build & Policy | Week 5 | Week 6 | Platform Build & Policy | Nov 02 2026 | Nov 13 2026
Configuration | Week 6 | Week 8 | Configuration | Nov 09 2026 | Nov 27 2026
Backup & Recovery Validation |  |  | Backup & Recovery Validation | Nov 30 2026 | Dec 11 2026
Knowledge Transfer |  |  | Knowledge Transfer | Dec 14 2026 | Jan 8 2027
Transition to Operations |  |  | Transition to Operations | Jan 11 2027 | Jan 22 2027
Stabilization & Final |  |  | Stabilization & Final | Jan 25 2027 | Feb 5 2027
Acceptance |  |  | Acceptance | Feb 8 2027 | Feb 12 2027
Estimated Timeline for Platform Recovery Runbooks
Activities | Target Start Date | Target End Date | Estimated Timeline for Enterprise Backup Platform
Recovery Scenario Definition | Nov 30 2026 | Dec 18 2026 | Activities | Target Start Date | Target End Date
Runbook Development | Jan 4 2027 | Jan 22 2027 | Requirements Defination | Oct 05 2026 | Oct 16 2026
Tabletop Walkthrough & Feedback | Feb 8 2027 | Feb 19 2027 | Backup Platform Design | Oct 12 2026 | Oct 30 2026
Finalization & Approval | Feb 22 2027 | Mar 05 2027 | Design Review and Approval | Nov 02 2026 | Nov 13 2026
Knowledge Transfer | Mar 8 2027 | Mar 19 2027 | Platform Build & Policy | Nov 16 2026 | Dec 04 2026
|  |  | Configuration | Nov 30 2026 | Dec 18 2026
|  |  | Holiday season | Dec 21 2026 | Jan 1 2027
|  |  | Backup & Recovery Validation | Jan 04 2027 | Jan 22 2027
|  |  | Knowledge Transfer | Jan 25 2027 | Feb 05 2027
|  |  | Transition to Operations | Feb 08 2027 | Feb 19 2027
|  |  | Stabilization & Final | Feb 22 2027 | Mar 05 2027
|  |  | Acceptance | Mar 08 2027 | Mar 19 2027

## Sheet2
Estimated Timeline for Enterprise Backup Platform
Activities | Target Start Date | Target End Date
Requirements Defination | Oct 05 2026 | Oct 16 2026
Backup Platform Design | Oct 12 2026 | Oct 30 2026
Design Review and Approval | Nov 02 2026 | Nov 13 2026
Platform Build & Policy | Nov 16 2026 | Dec 04 2026
Configuration | Nov 30 2026 | Dec 18 2026
Holiday season | Dec 21 2026 | Jan 1 2027
Backup & Recovery Validation | Jan 04 2027 | Jan 22 2027
Knowledge Transfer | Jan 25 2027 | Feb 05 2027
Transition to Operations | Feb 08 2027 | Feb 19 2027
Stabilization & Final | Feb 22 2027 | Mar 05 2027
Acceptance | Mar 08 2027 | Mar 19 2027
Estimated Timeline for Platform Recovery Runbooks
Activities | Target Start Date | Target End Date
Recovery Scenario Definition | Nov 30 2026 | Dec 18 2026
Runbook Development | Jan 4 2027 | Jan 22 2027
Tabletop Walkthrough & Feedback | Feb 8 2027 | Feb 19 2027
Finalization & Approval | Feb 22 2027 | Mar 05 2027
Knowledge Transfer | Mar 8 2027 | Mar 19 2027