## Slide 1
Agenda — Enterprise Backup Platform Client Kickoff
Today’s session: align the assessment scope, requirements, timeline and next steps
01
Kickoff Objective & Current State
Current Azure-native backup baseline, assessment purpose and client context.
02
Assessment & Requirements — Scope of Work
Assess third-party backup coverage and controls; define assumptions, constraints, dependencies and requirements.
03
High-Level Assessment Timeline & Alignment
Analysis, requirements gathering, recommendations and high-level schedule aligned to the approved Mid-Feb deployment timeline.
04
RACI & Responsibilities
Clarify Resilience Support Team and HPE responsibilities for assessment, requirements, reviews, inputs and sign-off.
05
Kickoff Discussion & Next Steps
Confirm scope, workshop topics, required access/data, owners and immediate actions.
KICKOFF OUTCOME
Agreed scope • Requirements baseline • Workshop plan • Client inputs / owners • Immediate next steps
1

## Slide 2
Enterprise Backup Platform — Client Kickoff
Resilience workstream | Assessment & requirements gathering
PRIMARY OBJECTIVE
Assess the current third-party backup environment, identify coverage and control gaps, and define the requirements and recommendations needed for next-step alignment.
REGIONAL MODEL
Canada Central
Primary production region
Canada East
Secondary DR / recovery target
1
Current state
Azure-native backup is currently in place Third-party backup environment is the assessment focus Existing Azure-native backup is used as the current baseline
2
Assessment focus
Coverage capabilities and controls Assumptions, constraints and dependencies Recommended objectives, architecture considerations and proposed implementation approach
DESIGN PRINCIPLE
Planning objective
Produce a high-level implementation schedule aligned to the currently approved Mid-Feb deployment timeline.

## Slide 3
Assessment & Requirements — Scope of Work
Assessment & Requirements — Scope of Work
Current Azure-native backups are in place; this phase establishes the gaps, requirements and recommended path forward.
3
Primary objective
Assess the current backup environment, define the requirements and produce the recommendations and high-level schedule needed to align with the approved Mid-Feb deployment timeline.
01
ASSESS
Current state & gaps
Assess the current state of the third-party backup environment, using the existing Azure-native backup foundation as the baseline.
Perform a gap analysis of coverage capabilities, controls and current-state practices.
02
DEFINE
Assumptions, constraints & dependencies
Document key assumptions, constraints and dependencies that could affect coverage, architecture, security, operations and delivery.
03
RECOMMEND
Objectives & architecture considerations
Develop recommended objectives, architecture considerations and a proposed implementation approach for the enterprise backup platform.
04
ALIGN
Implementation schedule
Produce a high-level implementation schedule and identify the activities, dependencies and decision points required to align with the currently approved Mid-Feb deployment timeline.
CURRENT SOW OUTPUTS
Current-state assessment + gap analysis • assumptions / constraints / dependencies • recommended objectives & architecture considerations • proposed implementation approach • high-level schedule aligned to Mid-Feb
RESILIENCE WORKSTREAM | ENTERPRISE BACKUP PLATFORM

## Slide 4
High-Level Assessment Timeline & Alignment
High-Level Assessment Timeline & Alignment
Current SOW focuses on assessment and requirements; dates below show the working sequence, with detailed planning to be confirmed.
4
Activity
Target Start
Target End
Key Milestone / Outcome
Analysis
Oct 05, 2026
Oct 16, 2026
Current-state assessment completed and findings documented.
Discussion on the Analysis
TBD
TBD
Findings reviewed; gaps, questions and priority focus areas confirmed.
Requirements Gathering
TBD
TBD
Assumptions, constraints, dependencies and requirements captured.
Requirements Sign-off
TBD
TBD
Requirements baseline agreed and ready for recommendation / planning.
Recommended Objectives / Architecture Considerations / Proposed Implementation Approach
TBD
TBD
Recommended objectives and approach documented for client alignment.
High-Level Implementation Schedule
TBD
TBD
Schedule and dependencies mapped to the approved Mid-Feb deployment timeline.
ALIGNMENT TARGET
High-level implementation schedule to align with the currently approved Mid-Feb deployment timeline. Detailed design and implementation remain subject to the next-phase CR.
RESILIENCE WORKSTREAM | ENTERPRISE BACKUP PLATFORM | CURRENT SOW

## Slide 5
RACI — Enterprise Backup Platform Workstream
Clear ownership for the current assessment and requirements-gathering scope.
HPE responsibility: provide timely access / data, participate in reviews and own procurement, licensing and subscription costs.
Workstream / Activity | Resilience Support Team | HPE
CURRENT SOW — ASSESSMENT & REQUIREMENTS |  | 
Kickoff, governance & schedule alignment | R | A
Provide access, inventory, documentation & data | C | R/A
Current-state third-party backup assessment & gap analysis | R/A | C
Assumptions, constraints & dependencies | R | C
Recommended objectives & architecture considerations | R | A
Proposed implementation approach | R | A
Requirements review & sign-off | R | A
High-level implementation schedule / Mid-Feb alignment | R | A
LEGEND
R
Responsible
A
Accountable
C
Consulted
I
Informed
Current SOW only. Detailed design and implementation are outside this phase.

## Slide 6
Kickoff Discussion — Proposed Agenda
Kickoff Discussion — Proposed Agenda
Focus the first workshop on the revised assessment and requirements SOW.
6
1
Current-state assessment scope
Confirm the Azure-native backup foundation, third-party backup assessment scope and environments / workloads to review.
2
Gap analysis & controls
Review coverage capabilities, recovery controls, security expectations and current-state gaps.
3
Assumptions, constraints & dependencies
Capture technical, operational, security, data residency and delivery dependencies.
4
Recommended objectives & architecture considerations
Align on desired outcomes, architecture considerations and the proposed implementation approach.
5
High-level implementation schedule
Confirm the planning assumptions and alignment needed to target the approved Mid-Feb deployment timeline.
6
Inputs, owners & next steps
Agree access / data requests, workshop participants, action owners and immediate next steps.
Expected outputs: agreed assessment scope • gap-analysis focus • requirements workplan • client inputs / owners • next-step actions
RESILIENCE WORKSTREAM | ENTERPRISE BACKUP PLATFORM | KICKOFF