## Sheet1
Operational Area | Option A — Existing Hub with ExpressRoute | Option B — New Dedicated Hub
Initial implementation | Low to Medium — reuse the existing hub, ExpressRoute connectivity, and firewall, subject to capacity and access approvals. | High — deploy the new hub and firewall, then design and implement private on-premises connectivity.
ExpressRoute connectivity | Low — connectivity to the on-premises data centre is already established. | High if a new circuit is required; Medium if existing connectivity can be shared through an approved architecture.
On-premises reachability | Low to Medium — validate routes, firewall rules, and workload requirements for access to on-premises services. | Medium to High — establish and validate end-to-end routing between the new hub, workload spokes, and on-premises networks.
Routing configuration | Low to Medium — extend existing routing and configure appropriate UDRs and peering. | High — design and validate routing between spokes, the new firewall, ExpressRoute connectivity, and on-premises networks.
Firewall policy management | Low to Medium — reuse existing policies where suitable; coordinate changes with the central network team. | Medium to High — manage dedicated firewall policies and ensure traffic between Azure and on-premises is inspected as required.
DNS and name resolution | Low to Medium — reuse existing DNS forwarding and resolution services if they support the workloads. | Medium to High — establish or integrate DNS forwarding and private name resolution so Azure workloads can resolve on-premises resources and vice versa, where required.
Access and permissions | Medium to High — access to the existing hub subscription and firewall may require approvals and coordination with another team. | Medium — establish RBAC and operational access for the new subscription; less dependence on the existing hub team.
Monitoring and troubleshooting | Low to Medium — leverage existing hub, firewall, and ExpressRoute monitoring where available. | Medium to High — monitor the new hub and firewall, plus the end-to-end path through ExpressRoute and on-premises networking.
Change management | Medium to High — changes must account for existing hub consumers and potential impact to shared connectivity. | Medium to High — the new hub can isolate some changes, but ExpressRoute, route advertisements, and on-premises dependencies may still require coordination.
High availability and resilience | Low to Medium — validate the resilience of the existing ExpressRoute, gateway, firewall, and hub design. | Medium to High — validate the availability of the new hub and firewall, and confirm whether the existing or new ExpressRoute architecture provides the required redundancy.
Security and isolation | Medium — shared infrastructure requires appropriate policy separation and controls to prevent unintended access between workloads. | Low to Medium operational overhead after setup — dedicated firewall and hub resources offer greater separation, but the team must configure and maintain the controls.
Ongoing operational ownership | Low to Medium — fewer new resources, but reliance on the central networking team remains. | Medium to High — greater ownership of the hub, firewall, routing, monitoring, and coordination with the ExpressRoute/on-premises teams.
Cost management | Low incremental overhead — existing connectivity and shared infrastructure may be reused, subject to capacity and chargeback arrangements. | Medium to High — additional hub and firewall costs; a new ExpressRoute circuit or gateway connectivity may add significant cost if required.
Overall operational overhead | Low to Medium | Medium to High, depending primarily on how on-premises connectivity is provided.

## Sheet2
Operational Area | Option A — Existing Central Hub | Option B — New Dedicated Hub
Initial implementation | Low to Medium — validate the existing hub, obtain access, configure peering, routing, and required firewall rules. | High — provision the subscription and hub resources, deploy Azure Firewall, configure networking, routing, logging, and security controls.
ExpressRoute connectivity | Low — connectivity to the on-premises data centre is already established. | High if a new circuit is required; Medium if existing connectivity can be shared through an approved architecture.
On-premises reachability | Low to Medium — validate routes, firewall rules, and workload requirements for access to on-premises services. | Medium to High — establish and validate end-to-end routing between the new hub, workload spokes, and on-premises networks.
Day-to-day management | Low to Medium — fewer new resources to manage, but changes must be coordinated with the existing hub's operational team. | Medium to High — your team manages a separate hub, firewall, routing, monitoring, and related resources.
Firewall policy management | Low to Medium — reuse existing policies where appropriate, but changes may require coordination to avoid affecting other workloads. | Medium — manage dedicated firewall rules and policies; more control, but your team owns the ongoing policy lifecycle.
Access and permissions | Medium to High — access to the existing hub subscription and firewall may require approvals and coordination with another team. | Medium — establish RBAC and operational access for the new subscription; less dependence on the existing hub team.
Monitoring and alerting | Low to Medium — leverage existing monitoring and logging if available and suitable. | Medium — configure and maintain monitoring, diagnostic settings, alerts, and dashboards for the new hub.
Patching and platform maintenance | Low to Medium — Azure Firewall is a managed service, but hub dependencies and any existing network appliances still require operational oversight. | Medium — Azure Firewall itself is managed by Azure, but your team owns the surrounding network configuration, policies, diagnostics, and troubleshooting.
Incident response and troubleshooting | Medium — incidents may require coordination across workload and central networking teams. | Low to Medium — clearer ownership of the dedicated hub, although workload-team coordination is still required.
Change management | Medium to High — changes must account for existing hub consumers and the risk of disrupting shared services. | Medium — changes can be isolated to the dedicated environment, with fewer shared-hub dependencies.
Capacity and performance management | Medium — validate existing firewall throughput, connection capacity, and impact from other workloads. | Medium — size and monitor the dedicated firewall based on workload demand; capacity planning remains your responsibility.
Governance and compliance | Low to Medium — reuse existing controls if they meet the AI workload's requirements; verify that policies and logging meet expectations. | Medium — implement and maintain subscription-level RBAC, Azure Policy, tagging, budgets, security controls, and compliance monitoring.
Resilience and recovery | Low to Medium — rely on existing hub design and resilience arrangements, subject to validation. | Medium — design and validate the new hub's availability, configuration recovery, and operational runbooks.
Ongoing cost administration | Low incremental overhead — existing connectivity and shared infrastructure may be reused, subject to capacity and chargeback arrangements. | Medium to High — additional hub and firewall costs; a new ExpressRoute circuit or gateway connectivity may add significant cost if required.
Overall operational overhead | Low to Medium, assuming the existing hub is suitable and access is granted. | Medium to High, because the new hub introduces additional resources and ongoing ownership responsibilities.