## ColocationFacilities-R&O
Colocation Facilities & Business Continuity – Risks and Observations
Area | Observation | Risk Level | Recommendation
Datacenter Operating Model | The Sault Area Hospital and Health Science North (Sudbury) datacenters operate in an Active/Passive configuration supporting 23 office Hospitals | Medium | Review long-term strategy to determine whether the current Active/Passive model aligns with business availability objectives and future growth requirements.
Critical Application Availability | Meditech Expanse is identified as a mission-critical application with a stated requirement for zero tolerance of unplanned downtime | High | Validate that current infrastructure, failover procedures, and recovery objectives support the application's availability requirements.
Disaster Recovery Failover | Failover to the secondary datacenter requires manual intervention and multiple operational activities during a site outage | High | Review and document failover procedures, identify automation opportunities, and conduct periodic failover testing.
Recovery Time Objectives | Documented RTOs exist for critical services including Meditech Expanse. However, actual failover execution complexity may impact achievement under real outage conditions | High | Validate that DR procedures, testing outcomes, and operational readiness consistently meet defined RTO targets.
Inter-Datacenter Latency Requirements | Meditech Expanse requires latency below 2 ms; datacenters are separated by approximately 310 km over a 10 Gbps dark fiber link. This physical separation may inherently limit the ability to consistently meet strict latency requirements for active workload mobility. | High | Option A: Engage ISP/dark fiber provider to validate whether path optimization (e.g., route engineering, direct wave services, or lower-latency optical path design) is possible to minimize latency within physical constraints and confirm if application requirements can be realistically achieved in the current architecture. Option B: Evaluate a strategic architecture shift for Meditech Expanse to a cloud-based DR or active standby model using a hyperscaler to reduce dependency on long-distance synchronous latency-sensitive inter-datacenter connectivity, and consider decommissioning or reducing reliance on the secondary physical DR site for this workload.
Geographic Separation | Datacenters are connected via a 10 Gbps dark fiber link spanning approximately 310 km | Medium | Periodically review bandwidth utilization, latency, and growth requirements to ensure continued support of critical applications and replication services.
Inter-Site Dependency | Business continuity, storage replication, disaster recovery, and application recovery processes depend on the availability of the inter-datacenter dark fiber connection | Medium | Review network resiliency, carrier diversity, and contingency procedures for inter-site connectivity failures.
DR Operational Readiness | The effort required to recover Meditech Expanse during a primary site outage has not been validated through discovery | High | Perform end-to-end disaster recovery testing and validate operational readiness against business expectations.
Business Impact | A prolonged outage of the primary datacenter could significantly impact clinical and operational services across all supported Hospital locations | High | Review business continuity plans and ensure recovery procedures are aligned with Hospitals criticality requirements.

## StorageComputeDataProt_R&O
Storage Compute & Data Protection - Risks and Observations
Area | Observation | Risk Level | Recommendation
Cyber Recovery Coverage | Cyber Recovery Vault and CyberSense currently protect only the Meditech application. | High | Assess additional critical applications for inclusion within the Cyber Recovery program.
Cyber Recovery Scope | Cyber recovery processes are limited to a subset of business services. | High | Establish a cyber recovery roadmap aligned to business-critical application tier services such as (AD, DNS, ADFS etc)
Cyber Recovery Site Dependency | Cyber Recovery Vault and CyberSense are deployed only in Datacenter A. | Low | Review cyber recovery strategy and determine whether geographic diversification is required to meet organizational recovery objectives.
Backup Platform Coverage | Dell NetWorker deployment is only identified in Datacenter A during discovery. | Low | Validate backup management architecture and confirm operational design.

## CiscoACI_R&O
Cisco ACI - Risks and Observations
Area | Observation | Risk Level | Recommendation
DCI Redundancy | DCI2↔DCI4 link is configured but not physically connected. Inter-pod communication currently relies on a single active DCI path (DCI1↔DCI3). | Medium | Activate and validate the secondary DCI path to provide full inter-site path redundancy.
Inter-Pod Bandwidth | Active inter-pod connectivity is limited to 10G between datacenters. | High | Validate bandwidth utilization against storage replication, DR recovery, workload mobility, and future growth requirements.
DCI Failover | Failover to the secondary DCI path requires manual intervention. | Medium | Review failover procedures and evaluate opportunities for automated failover.
DR Readiness | Disaster recovery testing frequency and failover validation were not reviewed during discovery. | Medium | Review DR test results, recovery procedures, and failback processes.
Storage and Network Dependency | PowerMax, RecoveryPoint, Data Domain replication, and VMware SRM rely on inter-datacenter connectivity; network capacity requirements have not been validated. | Medium | Validate network capacity and resiliency against recovery objectives and replication workloads.

## ADFS_R&O
Active Directory, Identity, File Services & Security – Risks and Observations
Area | Observation | Risk Level | Recommendation
Server OS Standardization | Mixed Windows Server 2019, and 2022 across environment | Medium | Standardize OS versions to reduce operational complexity, improve security posture, and simplify lifecycle management. Microsoft ended mainstream support for Windows server 2019 on January 9, 2024, with extended support continuing until January 9, 2029. To maintain supported and current OS platform, it is recommended to perform in-place upgrade of Windows server 2019 systems to Windows server 2022 wherever possible. An in-place upgrade is preferred over a side-by-side migration because exsisting applications, including MEDITECH, do not need to be reinstalled and server names remain unchanged reducing implementation effort and risk. To start with attempt with lower-tier and non-production servers to validate the upgrade process before proceeding with production servers. NOTE: For Active Directory Domain controllers running Windows server 2019, a side-by-side migration strongly recommended instead of an in-place upgrade. Deploy new Windows server 2022 Domain controllers, Configure DNS and other services and transfter the FSMO roles, verify the replications and then decommision the legacy Domain controllers.
Trust Model Complexity | Individual external trusts per Member site domain | Medium | Evaluate trust consolidation or modernization (e.g., identity federation or centralized trust model) as Member sites increase.
Single Forest Dependency | Entire enterprise identity depends on OneHits forest | Medium | Ensure robust forest recovery planning and periodic disaster recovery testing for identity services.
Active Directory Cyber Recovery Coverage | Domain Controllers are not currently included with Cyber Recovery vault or CyberSense protection scope | Medium | Evaluate inclusion of Active Directory within Cyber Recovery strategy to support identity recovery during cyber events.
File Distribution Dependency | Centralized SMBv3 file distribution model | Low | Monitor performance and scalability for large MEDITECH and operational file exports to Member sites.
Single Point of Failure in File Services | Certain file server components are not deployed in a fully redundant HA configuration due to MEDITECH architectural constraints | High | Engage MEDITECH vendor to redesign file service dependency model and introduce HA-compatible architecture where possible.
Cross-Environment Dependency (Prod ↔ Non-Prod) | Production transaction services depend on training/test environment components | Critical | Immediately isolate production workloads from non-production dependencies; validate architecture boundaries with MEDITECH.
Maintenance Impact on Production | Patching or rebooting non-production systems impacts production services | High | Implement dependency mapping and decouple shared services to ensure production isolation.
Member Sites Downtime During Maintenance | Member Sites experience service interruption during backend maintenance windows | Medium | Introduce HA file service layer or replication-based access model to reduce dependency on single systems.
MEDITECH Architectural Constraint | Application design enforces tight coupling between tiers and limits infrastructure-level HA implementation | High | Conduct joint architecture review with MEDITECH vendor to identify supported HA patterns and redesign options.
Lack of Service Isolation | Shared services between environments introduce unintended production impact | Critical | Enforce strict environment segmentation (Prod vs Non-Prod) at compute, storage, and network layers.
ADFS Dependency | Federated identity relies on ADFS infrastructure | Medium | Ensure high availability and evaluate long-term modernization path (e.g., cloud identity integration).
Trust Onboarding Dependency | Member site onboarding requires VPN + compliance validation | Low | Maintain governance framework and periodically validate onboarding checklist effectiveness.
Network Dependency | Trust relationships rely on stable site-to-site VPN connectivity | Medium | Ensure redundancy and monitoring of VPN infrastructure to avoid identity service disruption.
Host-Based Firewall Security | Windows Firewall is disabled across all servers to support MEDITECH application port and service requirements | High | Reintroduce host-based firewall controls using application-aware ruleset design, allowing only required MEDITECH ports/services while blocking all non-required traffic.
Application Dependency on Open Ports | MEDITECH architecture requires broad inter-server communication across multiple services and ports | High | Engage MEDITECH vendor to define minimal required port matrix and implement least-privilege network segmentation.
Loss of Host-Level Defense-in-Depth | Disabling Windows Firewall removes a key layer of endpoint protection within server operating systems | High | Implement compensating controls such as network segmentation, micro-segmentation, and internal firewalling at virtual switch or distributed firewall layer (e.g., VMware NSX or ACI policy).
Compliance & Security Posture | Disabled host firewall may not align with baseline security frameworks (e.g., CIS benchmarks) | Medium | Document exception formally and align with security baseline exception governance process.

## MEDITECH_PrintArchitecture_R&O
MEDITECH Print Architecture - Risks and Observations
Area | Observation | Risk Level | Recommendation
Central Print Server Dependency | MEDITECH print services are centralized through datacentre - hosted print server (s) | Medium | Validate whether print server high availablity, clustering or recovery mechanisms are in place.
VPN Dependency | Member Sites printing relies on active VPN connectivity to ONE HITS datacenter | Medium | Ensure VPN Monitoring, redundancy, and documented trobuleshooting procedures exist.
WAN Dependency | Print delivery dependent on network path between ONEHITS and Member sites | Medium | Validate WAN resiliency and bandwidth capacity for critical printing workflows.